## Summary
By the beginning of: | Summary of tasks
March | PSSs approved, development environments working and placeholder content committed
April | Resource proposals complete, strawman resource available for review and building upon
May | Core content ready for QA review and critique, open issues identified
June | Core elements agreed, content ready for polishing and alignment with QA requirements
July | Content is ready for final QA, editorial and format adjustment, publishing prep
August | Content is implementation ready, DSTU ballot opens

## Details
Task | Draft | Complete
Owner & reviewing WGs identified |  | March
gForge committers identified and granted permissions |  | March
PSS approved for owning WG |  | March
Resource name | March | April
Resource definition provided | March | April
Resource scope identified | March | April
Content sources identified | March | April
Example uses identified covering boundaries of intended scope | April | May
Search criteria identified and defined | April | May
Core data elements defined (names, types, cardinality, must understand, short descriptions) | April | May
One example instance created |  | May
Core element definitions (final = following QA guidelines) | May | July
Core element bindings | May | July
Core data element requirements and Usage Notes | May | July
Value set definitions and code lists | May | July
Invariants defined (Draft = English only is ok, Final = xpath needed) | May | July
Resource Introduction and additional guidance HTML | May | July
Mappings created for all source specifications, including RIM (Draft = non-formal) | May | July
Example instance created for all example uses exercising all data elements and repeatability at least once |  | July
UML diagram renders without crossing lines |  | July
Data elements are sorted appropriately based on importance/relatedness |  | July
Names consistent across resources where appropriate |  | July
Aliases defined for resource and elements |  | July
To dos all resolved |  | July
Open issues formally documented for consideration by DSTU implementers |  | July